## Overview
CodeRabbit - PoV & Mutual Success Plan
CSAA DPT working draft. Updated October 23, 2026. Dates, scope and commitments require joint confirmation.
THE PLAN AT A GLANCE
Customer | CSAA Digital Payment Transformation (DPT)
PoV start date | TBD. Per-platform enablement after vendor-risk clearance and locked probe-wave readiness.
PoV end date | TBD. Proposed three weeks after each platform is enabled. Record any approved extension or earlier stop.
Weekly Check In | Proposed weekly. Day/time TBD. Amit Mishra owns the mandatory Week 1 checkpoint per platform.
Executive readout date | TBD. Proposed end of Week 3: DPT evidence compilation, Enterprise Architecture review and ARC outcome.
Participating developers (#) | TBD. Confirm eligible developers, actual pilot participants and repository counts separately by platform.
Git Provider | Bitbucket Cloud for TPS, Payment Central and Informatica. Sanitized <source-repo>-aicr evaluation repos; mmani-csaa is tracking only, with reviews disabled.
Issue Tracker | Jira projects and linked-ticket conventions TBD. Confluence/specification sources and frozen revisions require confirmation.
MCP Integrations | TBD. Approved read-only external context, source permissions, egress and provider/plan support must be validated. SharePoint/other-source route is not assumed available.
Platform scope | TPS: Python/AWS serverless, RDS and Glue. Payment Central: legacy Java/on-premise. Informatica ETL: readable mappings/workflows and feed/restart semantics. Advisory review; human approval/merge retained.
STAKEHOLDERS
Team | Role | Name | Email
Customer | CTO | TBD. Confirm named CTO | TBD
Customer | Project Lead | Amit Mishra. Runbook responsibility; formal title TBD | TBD
Customer | Technical Lead | TPS: Sasi, Kasa, Sadak. Payment Central: Karthikeyan Subbiah. Informatica: Ashin. Primary contacts/titles TBD | TBD
Customer | Security / vendor-risk lead | TBD. Confirm accountable contact | TBD
Customer | Executive Sponsor | TBD. Confirm funding/escalation owner | TBD
Customer | Decision forum | Enterprise Architecture review; ARC final forum. Individual representatives TBD | TBD
CodeRabbit | Account Executive | TBD. Confirm account owner | TBD
CodeRabbit | Solutions Engineer | TBD. Confirm technical PoV owner | TBD
CodeRabbit | Executive Sponsor | TBD. Confirm sponsor | TBD
Evaluation basis | DPT v2.5 runbook | PI candidates | Proposed prompts and limits
Tracking | mmani-csaa | Formal results | Not yet evaluated
Plan status | Draft for joint confirmation | Updated | 2026-10-23

## Success Criteria
Success Criteria
DPT v2.5 is authoritative. Required criteria are High priority. Score each platform independently; retain native/configured results separately. All outcomes are pending.
Success Criteria | Measurement | Notes | Outcome
Codebase Context Depth | G4/P2: demonstrate a finding that depends on unchanged callers, shared code, tests, lockfiles or configuration. Cite the contextual artifact and explain the causal connection to the changed behavior. | High. File availability alone is not proof of use. A correct inline comment can be anchored to a changed line. Record inaccessible required context. | Not yet evaluated
Cross-Repo Context | P3/E1: use the approved, frozen separate spec repository. Distinguish a code violation from a missing/ambiguous spec. Use requirements.md for acceptance criteria, OpenAPI for contracts and ADRs for decisions, respecting phase/status. | High. For TPS, confirm csaa-tps-specs-wiki and the approved revision. Propose a concrete code/test action or spec clarification. Do not invent requirements. | Not yet evaluated
External Context Ingestion | A4/E2: retrieve and apply the linked ticket and approved design/acceptance context. Cite the source/version. Record any required retrieval failure and its effect on the assessment. | High. A4 is required core. E2 is NA only when the change has no linked ticket. Confirm Jira, Confluence, SharePoint/other routes, permissions and frozen sources; PIs cannot create access. | Not yet evaluated
Global & Repo Specific Configuration | A5/R1-R6: lock a tool-independent platform rule profile, translate approved rules into supported configuration and test positive cases/decoys. Verify path/module scope, approved exceptions and retention over time. | High. Report the configured round separately. R-set is NA until its profile is locked; inability to apply an applicable locked rule is a failed result. Budget about one configuration person-day per platform. PI library linked on Overview. | Not yet evaluated
Review Signal Quality | P1/P5-P10: useful replay signal >=40% of completed comparable P1 cases; P5/P6/P7 Green; silent noise control or at most 2 low-impact comments without claimed risk; P9 overlap >=80% on independent identical-input runs. P10 captures complete actionable finding evidence. | High. Verify hallucination resistance, origin and not-assessable honesty. Preserve raw file/location/severity/category/rationale/origin/action. Freeze configuration/context, use full/fresh runs, record duplicate/not-assessable counts and define empty denominators. Bands are calibration aids. | Not yet evaluated
Pre-PR & Agent Workflow | G7/G8/A1-A3: demonstrate approved local pre-PR/agent-usable output, a feedback handoff without rewriting, cross-task consistency against shared contracts, and severity calibrated to tests/tools/payment impact. | High. Inspect the actual public export and proposed patch. Preserve the human approval boundary. A text prompt does not add an export field or authorize autonomous code changes. | Not yet evaluated
Bitbucket, Security & Human Control | G1-G3/G5-G6: prove normal Bitbucket Cloud PR operation, advisory/non-blocking behavior, least-privilege roles/scopes and written data-handling answers. Test denied approval/merge/push/bypass effects and document egress, retention, deletion, subprocessors, model/provider and training usage. | High. Day 0-2 gate evidence is mandatory. Recorded POC SaaS-egress risk acceptance does not replace G5/G6 execution. Required gate failure stops or escalates the platform evaluation. Prompts are not permission controls. | Not yet evaluated
Change-Risk Tests & Failure Safety | P11-P13: identify the change-specific untested edge/failure/state transition, explain a plausible concurrency interleaving or atomicity failure, and preserve correct boundary handling, correlation, retries and DLQs. | High. Require a concrete cause and appropriate control. Avoid generic coverage demands, try/catch everywhere, duplicate logging and unsafe retries. The evaluator's harness proves the planted risk; a PI does not run the test suite. | Not yet evaluated
Payment, Contract & Platform Risk | Run applicable D1-D9, C1-C8 and A probes. TPS includes P4 and core S1/S5/S8/S10; preselect other S probes. Cover Payment Central transaction/legacy risks and readable Informatica mapping/feed/restart semantics where reviewable. | High for applicable core. Preserve Snyk provenance and assess added AI signal on identical commits. Do not apply AWS-only rules to on-premise platforms. Binary/unavailable ETL artifacts need a reviewability decision, not a prompt workaround. | Not yet evaluated
Adoption, Trust & Business Value | During approved Weeks 2-3 live use, classify findings independently. Initial Phase 4 Green bands: actionable >=60%, false positive <20%, no harmful finding observed. Measure reviewer load and end-window trust against the platform baseline. | High. Denominator excludes Duplicate and Not assessable; Partially actionable stays separate. Accepted high-risk advice receives a second human look. Resolve live-use authorization first. Usage and acceptance counts are not quality scores or measured ROI. | Not yet evaluated
Pilot Readiness & Decision | Amit Mishra owns the Week 1 continue/constrain/pause/stop decision per platform. End Week 3: DPT compiles evidence, Enterprise Architecture reviews and ARC receives the platform outcome under runbook section 19. | High. Outcomes: Ready to pilot now; Fix named blockers, then pilot; Limited use only; Do not proceed. Preserve NA/untested/invalid distinctions and frozen results. Acted-on harmful advice on payment/contract/security/irreversible paths triggers Do not proceed. Commercial approval is separate. | Not yet evaluated

## Milestone Tracker
Milestone & Activity Tracker
Proposed relative schedule. Calendar dates are TBD. Blank status means unconfirmed; In progress may mean a draft exists and does not imply customer acceptance. Owner roles require confirmation.
Phase | Milestone | Target Date | Status | CodeRabbit Owner | Customer Owner | Notes / Outcome
Pre POV Planning
Pre-PoV | Intro / Discovery call |  |  | TBD (account owner) | Amit Mishra | Requirements are available. Confirm discovery completion, attendees and date; no meeting completion is inferred.
Pre-PoV | Product Demo |  |  | TBD (technical owner) | Platform leads | Demonstration assets exist in tracking. Confirm the customer demo, audience and feedback; demonstration observations are not formal CSAA gate results.
Pre-PoV | Align on Business Value Assessment |  | In progress | TBD (account owner) | Amit Mishra / platform leads | Draft measurement definitions are mapped. Capture the three-month PR/reviewer-load baseline. Salary, developer counts, review-time reduction and defect economics require customer inputs; no ROI is asserted.
Pre-PoV | Agree teams, repositories and evaluation cohort |  | In progress | TBD (technical owner) | Platform leads | TPS, Payment Central and Informatica are the candidate platforms. Confirm exact code/spec repos and participants; create sanitized <source-repo>-aicr copies. Resolve disposable-only versus live Phase 4 policy.
Pre-PoV | Agree success criteria and PoV plan |  | In progress | TBD (technical owner) | Amit Mishra | This spreadsheet is the current plan; joint acceptance is pending. Lock waves, independent scorers and answer keys outside tool context. Resolve NA/not-tested semantics and any policy exceptions before execution.
Pre-PoV | Agree evaluation communication channel |  |  | TBD (account owner) | Amit Mishra | Confirm the approved channel, participants and evidence/escalation process. No Slack channel creation or notification is assumed.
Senior Testing & Configuration
Pre-PoV | Senior developers and leads: workflow / evidence briefing |  |  | TBD (technical owner) | Platform leads | Brief independent scorers on locked cases, origin labels, missing-context honesty, finding classification and the human-control boundary. Nobody scores a case they wrote.
Day 0-2 | Install approved pilot repositories and validate G1-G8 |  |  | TBD (technical owner) | Security / platform leads | After risk clearance and readiness: confirm service account, scoped credentials, egress, effective settings and written data-handling records. Preserve advisory review; record actual denied-action checks and public export/pre-PR output.
Week 1 | Complete native probes and Week 1 checkpoint |  | Not started | TBD (technical owner) | Amit Mishra | Run applicable P1-P13 and A4/E2 with the frozen native manifest. Capture completed, independent runs and raw findings. Amit decides continue / constrain / pause / stop per platform with EA/evidence input.
Weeks 1-2 | Domain cases and separate configured-rule round |  | Not started | TBD (technical owner) | Platform leads | Run applicable D/C/A/S and PC/IN cases. Lock each R1-R6 profile; select general PI/custom-check candidates in a new manifest, about one configuration person-day per platform. Preserve original results and record effort/residual gaps.
Broader Roll Out & Testing
Week 1 | User demo for the approved PoV cohort |  |  | TBD (technical owner) | Platform leads | Confirm participants, reviewer/agent workflow and evidence capture. Broader enablement remains conditional on the Week 1 decision and approved scope.
Weeks 2-3 | Enable approved cohort repositories and users |  | Not started | TBD (technical owner) | Security / platform leads | Enable only approved repositories/users after the checkpoint. Resolve live-PR authorization first; record cohort/window limits. Never enable review on the mmani-csaa tracking repository.
Weeks 2-3 | Weekly progress and evidence check-ins |  | Not started | TBD (technical owner) | Amit Mishra / platform leads | Track PR count/size, actionability, false positives, duplicates, not-assessable findings, reviewer load and confounds per platform. Give accepted high-risk advice a second human review. Record changes and incidents.
Feedback & POV Read Out
Week 3 | Developer sentiment retrospective |  | Not started | TBD (technical owner) | Platform leads | Use runbook Appendix C once at the end of the window. Record not measured if the retrospective is absent. Include usability, trust, harmful findings and senior triage effort; sentiment does not override required gates.
Week 3 | Score success criteria from independent evidence |  | Not started | TBD (technical owner) | DPT evidence owner / EA | Score locked cases 0-3 with the runbook outcome rules. Separate native, configured and remediation results and NA/not-tested/invalid states. Do not combine scores or average platforms. Preserve original failures and misses.
Week 3 | Executive readout and business value assessment |  | Not started | TBD (account owner) | Amit Mishra / EA / ARC | Present evidence-based per-platform recommendations, open blockers, setup effort and unmeasured value. Extend only for named missing evidence under recorded approval. Contract/purchase decisions remain separate.
Vendor Selection & Purchasing
Post-PoV | Vendor selection decision (conditional) |  |  | TBD (account owner) | TBD (sponsor) | Only after applicable pilot-entry rules and customer decision. Do not assume vendor selection, purchase or rollout from this working plan.
Post-PoV | Commercial terms (conditional) |  |  | TBD (account owner) | TBD (procurement) | Confirm actual seat/cohort scope, quote and commercial approvals separately. No price, savings or commitment is supplied.
Post-PoV | MSA review (conditional) |  |  | TBD (account/legal) | TBD (legal/security) | Confirm legal owners and required agreement review only if proceeding. This plan does not accept terms.
Post-PoV | MSA approval (conditional) |  |  | TBD (account/legal) | TBD (legal approver) | Customer approval and signatory authority remain unconfirmed; no approval is inferred.
Post-PoV | Order form signature (conditional) |  |  | TBD (account owner) | TBD (signatory) | Separate authorized commercial action. No contract start date or signature commitment is established.
Post-PoV | Pilot / production rollout plan (conditional) |  |  | TBD (technical owner) | TBD (rollout owner) | Agree scope, owners and retention/evaluation-copy cleanup only after entry rules are met. Re-run named fixes under new manifests on the same locked assets and preserve original evidence.

## Configuration Checklist
Configuration Checklist
Task | Docs | Status | Owner | Notes
Pre-Configuration
Confirm Bitbucket setup authority and runtime scopes | https://docs.coderabbit.ai/platforms/bitbucket-cloud |  | TBD (Security/admin) | Separate one-time workspace/repository installation authority from the ongoing service-account role and token scopes. Obtain approval for least privilege; verify effective denied actions and G3/G5. Do not assume standing admin is required for review.
Install on approved sanitized repositories only | https://docs.coderabbit.ai/getting-started/quickstart |  | TBD (platform/admin) | Confirm the code/spec inventory and <source-repo>-aicr evaluation copies. Do not install or enable reviews on mmani-csaa. Production/live-use scope needs explicit policy resolution.
Disable automatic review until controlled enablement | https://docs.coderabbit.ai/configuration/auto-review |  | TBD (technical owner) | Use explicit/manual runs for frozen probes as approved. Declare automatic/incremental behavior for the adoption cohort. The tracking repository remains excluded with automatic reviews disabled.
Assign seats to confirmed pilot users only | https://docs.coderabbit.ai/management/seat-assignment |  | TBD (account/admin) | Participant count, eligible population, actual users and entitlements are TBD. Confirm pilot scope and commercial terms separately; no seat count is assumed.
Phase 1 - Configuration
Set and freeze the review profile | https://docs.coderabbit.ai/reference/configuration#param-profile |  | TBD (technical owner) | Predeclare the native profile and all effective overrides. A later quieter profile is a configuration/remediation change; preserve the original noise and quality results.
Inventory coding guidelines and approved standards | https://docs.coderabbit.ai/knowledge-base/code-guidelines |  | Platform leads / CR TBD | Identify automatically discovered guideline files, versions and scope. Do not leak locked answer keys or load new house rules into the native round without declaring them. R profiles require owner approval.
Configure review paths and verify required context | https://docs.coderabbit.ai/configuration/path-instructions |  | Platform leads / CR TBD | Confirm readable code, IaC, tests, manifests/lockfiles and Informatica exports. A PI cannot override an excluded path. Do not remove must-find cases to lower noise; validate both reviewed scope and context availability.
Link approved code and specification repositories | https://docs.coderabbit.ai/knowledge-base/multi-repo-analysis |  | Platform leads / CR TBD | Confirm approved Bitbucket code/spec repos, frozen source revisions, requirements.md/OpenAPI/ADR roles and phase/status. Record provider/plan branch-selection limits and the actual supplied snapshot.
Define actionable PR output and evidence capture | https://docs.coderabbit.ai/getting-started/yaml-configuration |  | TBD (technical owner) | P10 needs actual file/location/severity/category/rationale/origin/action and agent handoff evidence. Comment-body guidance can help; it cannot add native export fields. Preserve raw output and mark adapter/unavailable fields explicitly.
Select path instructions for a separate configured round | https://docs.coderabbit.ai/configuration/path-instructions | In progress | Platform leads / CR TBD | Candidate library prepared October 23, not applied or validated. See Overview link. Replace illustrative globs, consolidate applicable rules and freeze a new manifest. P8: normally no finding for proven non-semantic changes; low priority only for useful optional formatting advice.
Establish the approved shared configuration baseline | https://docs.coderabbit.ai/configuration/configuration-inheritance |  | TBD (technical owner) | Inventory inheritance/global overrides, learnings, enabled tools and external sources. Export the effective result. Prompt text is not a permission boundary; approved provider controls must enforce human authority.
Freeze per-repository configuration manifests | https://docs.coderabbit.ai/getting-started/yaml-configuration |  | Platform leads / CR TBD | Record code/spec SHAs, tool/CLI version, profile, path rules, sources, scopes, review mode and approved exceptions per platform. Preserve native, configured and remediation manifests/results separately.
Phase 2 - Broader Team Roll Out
Trial Change Stack in the approved workflow | https://docs.coderabbit.ai/pr-reviews/change-stack |  | TBD (technical owner) | Confirm provider/plan availability and usefulness on actual Bitbucket pilot work. This optional enablement item does not replace any required gate or probe.
Validate review commands and independent reruns | https://docs.coderabbit.ai/guides/commands |  | TBD (technical owner) | Use actual completed full reviews or supported CLI fresh mode for independent P9 repeats; log reused/skipped/partial/failed runs. Freeze context and configuration and predeclare the both-empty overlap rule.
Control learnings and knowledge-base sources | https://docs.coderabbit.ai/knowledge-base/learnings |  | TBD (technical owner) | Inventory evolving learnings and source revisions. Local scope is not an immutable freeze. Do not reset a shared organization's knowledge casually; isolate the approved evaluation setup and record residual variation.
Validate the approved CLI / IDE / agent route | https://docs.coderabbit.ai/cli/reference |  | Platform leads / CR TBD | Actual IDEs, agents and managed installation are TBD. Demonstrate G8 and A2 through a supported local route with structured raw output, terminal completion and human-approved proposed repairs.
Validate dashboard and raw findings export | https://docs.coderabbit.ai |  | TBD (technical owner) | Confirm actual provider/plan metrics, export fields and provenance. Dashboards support evidence; independently classified findings and locked-case results are primary. Do not treat usage or acceptance as actionability.
Phase 3 - Advanced Governance & Context
Define warning-mode custom checks where appropriate | https://docs.coderabbit.ai/pr-reviews/custom-checks |  | Platform leads / CR TBD | Use approved general invariants in a declared configured round. A custom-check summary is distinct from inline review and cannot run the application test suite, enforce G3 or alone satisfy P10.
Connect approved issue-tracker context | https://docs.coderabbit.ai/integrations/issue-integrations |  | TBD (source owner) | Confirm Jira projects, linked-ticket conventions, access, frozen references and data handling. A4 is core; E2 is NA only without a linked ticket. Required-context retrieval failure must be recorded.
Validate approved read-only MCP / external context | https://docs.coderabbit.ai/knowledge-base/mcp-context |  | Security / source owner TBD | Confirm whether approved external context is needed and supported. Enumerate tools/data hops, constrain credentials, test denied writes and protect against embedded instructions. A PI cannot create a connector, permission or immutable snapshot.

## PR Feedback
PR Feedback
Log real findings only. Preserve raw severity/output and manifest ID. Independently classify Useful? and False positive?. Record duplicates, not-assessable findings and harmful acted-on advice in notes. Demonstration findings are not customer PoV results.
PR link | Repo | Severity | Useful? | False positive? | Action / tuning | Evidence / evaluator notes | Origin / manifest

## BVA Inputs
BVA Inputs
CSAA inputs are pending. Template sample assumptions have been cleared. Blank values are unknown, not zero; calculated savings remain blank until required inputs exist.
Input | Value | Measured / Modeled | Source / assumption note
SENIOR DEVELOPER TIME SAVED
Avg FTE salary |  |  | TBD. CSAA fully loaded senior salary and currency for the eligible cohort; no accepted amount supplied.
# senior developers |  |  | TBD. CSAA eligible senior developers; distinguish actual participants from total population.
Annual cost of senior devs
% dev time on code reviews |  |  | TBD. Measure review effort from the platform's three-month baseline; no review-time percentage is agreed.
Yearly cost of code reviews
Review-time reduction by CodeRabbit |  |  | TBD. Measure change in senior review/triage effort against the same cohort baseline. No 25% reduction is assumed.
Senior time-saved savings
JUNIOR DEVELOPER TIME SAVED
Avg FTE salary |  |  | TBD. CSAA fully loaded junior salary and currency; no accepted amount supplied.
# junior developers |  |  | TBD. CSAA eligible junior developers; no population count is assumed.
Annual cost of junior devs
% dev time on code reviews |  |  | TBD. Customer baseline for junior review-related effort; keep its definition consistent with follow-up measurement.
Yearly cost of code reviews
Review-time reduction by CodeRabbit |  |  | TBD. Measure junior effort change; no reduction factor or savings target has been accepted.
Junior time-saved savings
QUALITY FIXING BUGS EARLY
PRs merged per month |  |  | TBD. Actual merged PRs per month for the scoped platform/cohort; use the Phase 0 inventory.
PRs merged per year
Avg bugs per PR caught & fixed |  |  | TBD. Independently verified distinct bugs fixed per scoped PR; do not use raw comment count as bugs.
Total bugs per year
% bugs reaching prod undetected without CR |  |  | TBD. Historical defect escape assumptions require CSAA evidence. TPS is not production-live; do not invent its incident history.
Yearly bugs reaching prod
Cost of fixing a bug in production |  |  | TBD. CSAA-supported cost per production defect, currency and scope; no generic $10,000 assumption.
Fixing-bugs-early savings
TOTAL
Total annual savings |  |  | A modeled potential annual benefit only after all inputs are approved. Avoid double-counting effort and defect costs; this is not measured ROI or a purchase justification.
Value targets are fewer material misses, lower senior triage/rework and sustained developer trust. Report per platform; no composite quality score or measured financial return is established.

## Metrics
Metrics
Capture CSAA baseline and PoV results separately per platform. Blank numeric inputs are not measured. Never blend native/configured or probe/live rates; usage and acceptance are context, not quality scores.
Metric | Baseline (pre-PoV) | PoV Result | Target | Source / How Measured | Notes
Active users |  |  | TBD cohort | Eligible-user roster and actual usage | Confirm population and active-user definition/window. Customer PoV values are pending.
PRs reviewed |  |  | Record scoped cohort | Bitbucket/CR run records | Count completed reviews and report skipped/reused/partial runs separately. Preserve PR-size spread.
PRs merged |  |  | Record same cohort | Bitbucket merge events | Use the same PR cohort/window as reviewed PRs; merges do not establish review quality.
% PRs merged |  |  | No quality target | Merged / reviewed in the same cohort | Blank if required inputs are missing or denominator is zero. Define cohort/cutoffs before comparison.
CR suggestions (total) |  |  | Record raw count | Raw export, reconciled to review records | Preserve duplicates and not-assessable counts separately. Comment volume is not a bug or quality measure.
# suggestions accepted |  |  | No agreed count target | Observed code/test/spec actions | Use actual acted-on evidence. Acceptance does not establish correctness; high-risk accepted advice needs a second human look.
Acceptance rate (overall) |  |  | No agreed rate target | Accepted / suggestions in same cohort | This is not actionable rate. Blank if input is missing or denominator is zero; keep source counts.
Acceptance rate - critical |  |  | Measure; threshold TBD | Raw severity and acted-on evidence | Record numerator/denominator and preserve vendor severity. Do not infer safety from acceptance.
Acceptance rate - major |  |  | Measure; threshold TBD | Raw severity and acted-on evidence | Same cohort/window and original severity; no measured customer result supplied.
Acceptance rate - minor |  |  | Measure; threshold TBD | Raw severity and acted-on evidence | Separate nits, duplicates and correct minor findings; raw acceptance is not actionability.
Review turnaround time |  |  | Improvement target TBD | Three-month baseline and matched PoV PR timing | Use consistent start/end events and report sample size, PR size and reviewer-load confounds.
PR cycle / merge time |  |  | Improvement target TBD | Bitbucket timestamps for the same cohort | Separate queue/review/author time where available. No causal productivity claim from a few PRs.
Defect escape rate |  |  | Target TBD by platform | Verified production defects / scoped delivery | Requires actual baseline and exposure period. TPS is not production-live; record true NA or not measured explicitly.
Per-PR incumbent cost vs. per-seat cost |  |  | Quote/scope TBD | Actual incumbent spend and approved CR quote | Align period, currency, users and PR cohort. Commercial comparison is separate from review-quality scoring.
Developer sentiment score |  |  | End-window retrospective | Runbook Appendix C survey | Record not measured if absent. Trust is supporting evidence; required gates and harmful-action stop rules still control.
Actionable finding rate |  |  | >=60% initial Green | Independent finding classification, runbook section 15 | Phase 4 denominator excludes Duplicate and Not assessable. Partially actionable is a separate rate. Report numerator/denominator; keep probe and live rates separate.
False-positive rate |  |  | <20% initial Green | Independent finding classification, runbook section 15 | Include harmful false positives once in the false-positive numerator and report harm separately. Same denominator as actionability; report per platform.
Harmful findings / near misses |  |  | None observed | Acted-on/near-miss review and senior intervention log | Harm count is a floor. One caught near miss is Yellow; multiple near misses or acted-on harmful advice trigger the runbook decision rules. Accepted high-risk advice gets a second look.
P1 useful replay signal |  |  | >=40% initial Green | Useful signal / completed comparable P1 cases | Use locked historical/seeded cases and independent scoring. Keep the actual case inventory and completed denominator.
P9 finding overlap |  |  | >=80% initial Green | Matched pairs / union, runbook section 15 | Independent identical-input full/fresh runs. Same issue/location; severity differs by at most one level. Retain both raw runs and matching sheet; define both-empty handling.
Configuration effort (person-days) |  |  | Plan about 1 person-day/platform | Actual setup/tuning effort log | Budget is not a measured result or cap. Separate native setup, locked R-profile configuration and later remediation.
Duplicate finding count |  |  | Report count separately | Independent distinct-finding classification | Several comments on one root cause count as one distinct finding; classify the extras as Duplicate and exclude them from the quality-rate denominator.
Senior reviewer triage / rework effort (hours) |  |  | Reduction target TBD | Phase 0 reviewer-load baseline and matched cohort | Measure hours spent finding issues and triaging AI advice separately. Do not assert salary savings before the CSAA inputs and effort change are established.
Not-assessable finding count |  |  | Report count separately | Independent missing-context classification | Exclude correctly not-assessable findings from quality-rate denominators, but retain their count and missing source. This does not make an untested required capability NA.